## Cover Page
Car Rental System
Prepared By:
Team 28
Sabil: 000006913
Sahil: 169068279
Ayesha: 169045751
Shalin: 169073107
Kritika Sunil: 000006996
Muhammad Mahad: 169077650
Moosa: 169046796

## Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
AUTH-1 | Secure Account Creation | As a new user, I want to create an account with my email and a secure password so that I can access the platform's features. | 3 | High | Sprint 1 | Completed | Email verification should be implemented for greater security. | User can create an account using their own email.
AUTH-2 | Secure Login & Logout | As a registered user, I want to log in and out securely so that my personal information and booking history are protected. | 2 | High | Sprint 1 | Completed | Personal information should be partially censored. | User can be logged in and browse their dashboard securely.
UI-1 | Vehicle Search | As a customer, I want to search for available cars by date and location on the homepage so that I can quickly see my options. | 3 | High | Sprint 1 | Completed | What is the minimum/maximum time frame and location range. | User can search for rentals on specific dates or time frames as well as location.
UI-2 | Vehicle Search Result Basic Information | As a customer, I want to see a list of available cars with key details (image, model, price) after searching so that I can compare my choices. | 5 | High | Sprint 1 | Completed | Decide how much information should be displayed. | User can search and get multiple results with important information displayed.
UI-3 | Detailed Vehicle Information | As a customer, I want to view a detailed page for a specific car with more images, full specifications, and total cost so that I can make an informed decision. | 5 | High | Sprint 2 | Completed | What to do if an entry does not have all the required information. | User can get all the required information they need about the current vehicle.
RES-1 | Shopping Cart | As a customer, I want to add a selected vehicle to a shopping cart so that I can finalize my booking without losing my selection. | 3 | High | Sprint 2 | Completed | Needs persistent tracking of shopping cart items between pages, as well as a maximum cart size. | Shopping cart can hold items and check them all out at once.
RES-2 | Reservation Payment & Confirmation | As a customer, I want to complete a reservation by providing payment details (simulated) so that my booking is confirmed. | 5 | High | Sprint 2 | Completed | Need to implement a payment system. | User can check out and receive confirmation of their booking.
USER-1 | Reservation Dashboard & History | As a registered user, I want a personal dashboard to view my current and past reservations so that I can manage my rental history. | 5 | Medium | Sprint 2 | Completed | Decide on how far reservation history goes back. | Display current and previous reservations, as well as being able to manage Current reservations.
ADMIN-1 | Administrator Login & Portal | As an administrator, I want to log into a separate admin portal so that I can manage the system's operations. | 3 | High | Sprint 2 | Completed | Need separate database of accounts for administrators. | Administrators can access a private portal, prompted with a login screen.
ADMIN-2 | Administrator Tools | As an administrator, I want to add, view, and update vehicle details in the fleet inventory so that the car listings are always accurate. | 8 | High | Sprint 2 | Completed | Need to make administrator changes show up on the user's end. | Updates to the database save and appear for all users.
UI-4 | Search Filtering | As a customer, I want to filter search results by car category and price range so that I can narrow down my options more effectively. | 5 | Medium | Sprint 3 | Sprint 3 | When filtering, need to take into account if the user used a custom time frame or location range search. | Search results are filtered to the user input.
REP-1 | Detailed KPI Report | As an administrator, I want to view a dashboard with key performance indicators (KPIs) like fleet utilization so that I can monitor business health. | 8 | Medium | Sprint 3 | Sprint 3 | KPI information should be able to be exported to Excel. | KPI information visible on the dashboard and downloadable.
PAY-1 | Payment System Implementation | As a developer, I need to integrate a simulated payment gateway to process transactions and finalize bookings. | 5 | High | Sprint 3 | Sprint 3 | Transactions and bookings should be used as data for KPI. | Bookings should be finalized only if the transaction is valid.
Milestone 02 should now include:
Story ID, Title, Card (User Story) – already from Milestone 01 (You may add, or break down some of the story)
Story Points – estimated effort (e.g., 1, 3, 5, 8 using Fibonacci scale)
Priority (High, Medium, Low)
Sprint – which sprint it belongs to (Sprint 1, 2, or 3), the original Sprint
Status – Not Started, In Progress, or Done
Conversation – clarifications or notes from team discussions
Confirmation – acceptance criteria (how to know the story is “done”)
Note: The Fibonacci scale is a system of Agile estimation that uses numbers from the Fibonacci sequence (typically 0, 1, 2, 3, 5, 8, 13, 21, etc.) to assign story points to user stories and tasks.
This scale reflects an exponential increase in effort for more complex tasks and helps teams account for the growing uncertainty in estimating larger work.

## Sprint 1
Sprint 1 Backlog
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
AUTH-1 | AUTH-1.1 | Design DB Schema | Create User table with email, hashed_password, and profile fields. | 4 | Completed | “Ensure password hashing is secure.”
AUTH-1 | AUTH-1.2 | Build Registration API | Create backend endpoint to handle user registration. | 6 | Completed | “Test for duplicate email handling.”
AUTH-1 | AUTH-1.3 | Create Registration UI | Develop frontend form for user sign-up. | 5 | Completed | “Add form validation and success message.”
AUTH-2 | AUTH-2.1 | Build Login API | Create backend endpoint for user authentication and session management. | 5 | Completed | “Verify session expiration logic.”
AUTH-2 | AUTH-2.2 | Create Login UI | Develop frontend form for user login. | 4 | Completed | “Connect with authentication API.”
UI-1 | UI-1.1 | Design Search UI | Create wireframe and implement the vehicle search form component. | 6 | Completed | “Review layout with UX team.”
UI-1 | UI-1.2 | Build Search API | Create backend endpoint to filter available vehicles by date/type/price. | 8 | Completed | “Optimize query filters for performance.”
UI-1 | UI-1.3 | Implement Search Results | Develop frontend component to display search results. | 7 | Completed | “Ensure results refresh dynamically.”
UI-2 | UI-2.1 | Design Details Page | Create wireframe and implement the vehicle details page component. | 5 | Completed | “Add responsive design for mobile.”
UI-2 | UI-2.2 | Build Details API | Create backend endpoint to fetch detailed vehicle information. | 3 | Completed | “Confirm vehicle info accuracy.”

## Sprint 2
Story ID | Task ID | Task Title | Task Description | Ideal | Status | Comments
AUTH-3 | AUTH-3.1 | Implement Secure Account Creation | Enhance registration flow with email verification for stronger security. | 6 | Completed | Add email verification before account activation.
AUTH-3 | AUTH-3.2 | Secure Login & Logout | Improve login/logout to ensure session security and data privacy. | 5 | Completed | Mask sensitive data and secure sessions.
UI-3 | UI-3.1 | Design Vehicle Search Filters | Create wireframe for search filters by time frame and location. | 5 | Completed | Align design with existing search layout.
UI-3 | UI-3.2 | Implement Search Filter Logic | Develop backend logic to filter vehicles by date and location. | 7 | Completed | Optimize database queries for faster results.
UI-3 | UI-3.3 | Display Basic Vehicle Information | Create frontend component to show summarized vehicle data. | 5 | Completed | Ensure consistent format with main search results.
UI-4 | UI-4.1 | Implement Search Filtering | Integrate advanced search filters on search results page. | 6 | Completed | Validate filter combinations and dynamic updates.
UI-4 | UI-4.2 | Update Search Results Display | Refresh displayed results when filters are applied. | 4 | Completed | Confirm correct filter results in all test cases.
UI-5 | UI-5.1 | Design Detailed Report Page | Create wireframe for downloadable vehicle report view. | 5 | Completed | Ensure layout supports export to Excel.
UI-5 | UI-5.2 | Build Detailed Report API | Create backend endpoint to generate detailed vehicle reports. | 6 | Completed | Verify report accuracy and export functionality.
RES-2 | RES-2.1 | Implement Reservation History View | Develop UI to show previous and current reservations. | 5 | Completed | Show reservation details with proper date formatting.
RES-3 | RES-3.1 | Build Reservation Cancellation API | Allow users to cancel past reservations and update records. | 4 | Completed | Ensure cancelled reservations reflect immediately.
ADM-1 | ADM-1.1 | Build Admin Login Portal | Create secure login page for administrators. | 5 | Completed | Validate login credentials with admin database.
ADM-2 | ADM-2.1 | Design Admin Dashboard | Create wireframe for managing user and vehicle records. | 6 | Completed | Include data visualization for quick access.
ADM-2 | ADM-2.2 | Implement Admin Data Management | Enable admin to update and delete vehicle/user information. | 7 | Completed | Ensure audit logging for all admin edits.
PAY-1 | PAY-1.1 | Integrate Payment Gateway | Connect system with secure payment gateway API. | 8 | Completed | Confirm transaction validation before booking.
PAY-3 | PAY-3.1 | Develop Payment System Backend | Build backend module for transaction recording and booking validation. | 6 | Completed | Handle transaction rollback on failed payment.
PAY-3 | PAY-3.2 | Design Payment Confirmation UI | Create UI screen to confirm booking success. | 4 | Completed | Display clear payment and booking summary.

## Sprint 3
Story ID | Task ID | Task Title | Task Description | Ideal | Status | Comments
Admin - 1 | ADM - 1.1 | Build Admin Login Portal | Create Secure login page for administrators; role validation; DB check | 5 | Completed | Validated login with admin DB
Admin - 2 | ADM - 2.2 | Implement AdmingData Management | CRUD + update/ delete vehicle/ user records; image handling | 7 | Completed | Audit logging added
UI - 4 | UI - 4.1 | Implement Search Filtering | Advanced search filter integration | 6 | Completed | Validated filters and dynamic updates
UI - 4 | UI - 4.2 | Update Search Results Display | Refresh results when filters are applied | 4 | Completed | Verified correct filter results
PAY - 1 | PAY - 1.1 | Integrate Payment Gateway | Connect payment form to backend booking logic | 5 | Completed | Confirmed transaction validation
REP - 1 | ADM - 2.1 | Admin Dashboard & KPI | Display KPIs, fleet usage, statistics | 8 | Completed | KPI visualization implemented

## Final Product backlog
Story ID | Title | Priority | Points | Sprint | Status
AUTH-1 | Secure Account | High | 3 | Sprint 1 | DONE
Creation
AUTH-2 | Secure Login & Logout | High | 2 | Sprint 1 | DONE
UI-1 | Vehicle Search | High | 3 | Sprint 1 | DONE
UI-2 | Search Results - Basic Info | High | 5 | Sprint 1 | DONE
UI-3 | Vehicle Details Page | High | 5 | Sprint 2 | DONE
UI-4 | Filter Search by Category/Price | Medium | 5 | Sprint 2 | DONE
USER-1 | User Dashboard | Medium | 5 | Sprint 2 | DONE
RES-1 | Shopping Cart | High | 3 | Sprint 2 | DONE
RES-2 | Reservation & Payment | High | 5 | Sprint 2 | DONE
ADMIN-1 | Admin Login Portal | High | 3 | Sprint 3 | DONE
ADMIN-2 | Vehicle Inventory | High | 8 | Sprint 3 | DONE
Management
PAY-1 | Payment Integration | High | 5 | Sprint 3 | DONE
REP-1 | Admin Dashboard & | Medium | 8 | Sprint 3 | DONE